## Project Status
Project Status Report: POC Doctrans
Team Members: Aryan, Tulika, Navneet
Status | Feature / Component | Detailed Description
Resolved | System Stability & Deployment | Successfully fixed frontend deployment blockers, resolving port conflicts and CORS security policies on Lightning AI.
Resolved | API Optimization | Diagnosed and eliminated critical UI rendering loops, preventing API rate-limiting errors (HTTP 429) and ensuring stable Gemini AI integration.
Resolved | Data Privacy (Zero-Storage) | Engineered a secure, in-memory processing pipeline that ensures no sensitive client data is ever saved to the server's hard drive.
In Progress | Word Document (.docx) Support | Upgrading the frontend UI and backend pipeline to accept and process Word files natively.
In Progress | Format-Preserving Translation | Implementing logic to surgically translate document text while keeping the original corporate formatting, logos, and watermarks 100% intact.
In Progress | Automated File Delivery | Developing a binary (Blob) download architecture so translated files automatically download to the user's machine without manual steps.
Upcoming | Intelligent Document Processing (IDP) | Expanding the AI pipeline to go beyond translation, automatically extracting structured insights like executive summaries and inclusion/exclusion criteria directly from the uploaded files.